## Process Register
Section | Process | Ideal | Current State | Implementation Plan
P1 — Customer Voice Capture
P1 | Orange microphone deployment | Visible orange mic at every customer interaction point. Unmistakable. Trust device, not surveillance device. | Not implemented | Procure orange clip-on/fixed microphones. Install at reception, consultation rooms, service desks. Position for visibility. Test customer sight lines.
P1 | On-premise processing hardware | Raspberry Pi or edge compute device at each location. Air-gapped from internet for voice data. | Not implemented | Deploy edge compute hardware per location. Configure air-gap networking — voice data pathways have no internet route. Test isolation.
P1 | Transcription engine | OpenAI Whisper running locally on-device. No cloud API calls. 95%+ accuracy clean conditions. WER <10% clean, <20% noisy. | Not implemented | Deploy Faster-Whisper (CTranslate2-optimised) on edge hardware. Benchmark accuracy against target WER. Tune for client's acoustic environment.
P1 | Acoustic feature extraction | Parallel extraction of pitch (F0), speech rate, volume (RMS), pause patterns, jitter, shimmer on every interaction. | Not implemented | Deploy Librosa on edge device. Build extraction pipeline running in parallel with transcription. Define feature vector schema. Store features alongside transcription output.
P1 | Speaker diarisation | Customer voice algorithmically separated from staff voice. 95%+ accuracy on distinct voices. | Not implemented | Implement speaker diarisation model. Train/calibrate on client-specific audio (staff voices registered, customer voices classified as unknown). Test accuracy.
P1 | Audio quality gate | Interactions with insufficient audio quality automatically discarded rather than producing unreliable analysis. | Not implemented | Define minimum audio quality thresholds (SNR, clipping, background noise levels). Build quality check step before analysis pipeline. Log discard rate.
P1 | Customer verbal notice | Customer verbally informed recording is active at the start of every interaction. | Not implemented | Script verbal notice for staff. Train staff on delivery. Include in onboarding materials. Audit compliance.
P1 | Signage at point of entry | Clear signage at business entry points reinforcing recording notification. Triple-layer consent: verbal + visual (orange mic) + signage. | Not implemented | Design and produce signage. Install at all entry points. Review wording with legal. Ensure visibility and readability.
P2 — Customer Sentiment Analysis
P2 | NLP text sentiment extraction | Sentiment extracted from transcribed customer speech using fine-tuned transformer model. Domain-specific (customer service). | Not implemented | Evaluate HuggingFace pre-trained sentiment models. Fine-tune on customer service domain data. Benchmark against manual annotation. Deploy on edge hardware.
P2 | Acoustic sentiment analysis | Paralinguistic features (pitch variability, speech rate changes, pause frequency, volume shifts, jitter/shimmer) analysed for emotional indicators. | Not implemented | Build acoustic analysis pipeline using Librosa + pyAudioAnalysis. Define composite scoring from acoustic features. Calibrate against known positive/negative interactions.
P2 | Weighted fusion scoring | Text sentiment + acoustic features combined using weighted fusion. Net Sentiment Score (NSS = % Positive - % Negative, range -100 to +100). | Not implemented | Design fusion algorithm. Determine optimal weights through A/B testing. Validate combined score against human judgment. Define NSS calculation.
P2 | Topic classification | Each interaction classified by topic (service quality, wait time, product knowledge, billing, etc.). | Not implemented | Build topic classification model. Train on client-specific interaction categories. Deploy as pipeline step after sentiment scoring.
P2 | Raw audio deletion | Raw audio DELETED immediately after processing. Zero retention. Physical enforcement — buffer overwritten. | Not implemented | Implement secure deletion in processing pipeline. Audio buffer overwritten upon completion. No archive, no backup, no exception (except P7 positive capture). Audit deletion compliance.
P2 | Transcription deletion | Transcription text DELETED after sentiment extraction. Only sentiment scores retained. | Not implemented | Build pipeline to extract sentiment/topics then purge transcription. Verify no residual text in any data store. Automated audit.
P2 | P2 anonymisation | Output is P2 anonymised — no customer identity recoverable from sentiment data. | Not implemented | Strip all identifying metadata before storage. No customer name, no phone number, no interaction ID linkable to individual. Test re-identification resistance.
P3 — Aggregate Intelligence
P3 | NSS calculation engine | Net Sentiment Score calculated and updated in real-time. Available as 7/30/90-day moving averages. | Not implemented | Build NSS calculation service. PostgreSQL for structured storage. Materialised views for moving averages. Real-time update on each new interaction.
P3 | Topic-sentiment matrix | Matrix showing what customers talk about x how they feel about it. Updated continuously. | Not implemented | Build cross-tabulation of topic classifications against sentiment scores. Visualise as bubble chart. Update hourly.
P3 | Temporal pattern detection | Day-of-week and time-of-day sentiment patterns identified and tracked. | Not implemented | Aggregate sentiment by day/time slots. Build heatmap visualisation. Identify recurring patterns. Flag Monday morning data as baseline noise (see P4).
P3 | Location/team comparison | Relative comparison across locations and teams by NSS. Not a league table — framed as 'where might teams benefit from support?' | Not implemented | Build location/team aggregation. Horizontal bar chart with trend indicators. Sort by score. Frame all labels as supportive, never competitive.
P3 | Sentiment gauge dashboard | Large NSS gauge with delta arrow showing change from previous period. Executive glanceable view. | Not implemented | Build D3.js or Plotly dashboard. Self-hosted on Docker/Traefik. Real-time gauge refresh. Daily trend lines. Event annotation capability.
P3 | Bubble chart visualisation | Topic bubbles: size = volume, colour = sentiment (green to amber to red). Click to drill into category. | Not implemented | Implement Leapsome-style bubble chart. Interactive drill-down. Filter by time period, location, team. No word clouds.
P3 | Heatmap visualisation | Day x time grid showing sentiment intensity. Reveals temporal patterns. | Not implemented | Build heatmap component. Colour intensity = sentiment strength. Filterable by location/team.
P3 | Filterable interaction feed | Scrollable list of anonymised interactions with sentiment tags, topic classification, key phrases. Filterable. | Not implemented | Build feed component. Ensure all entries are anonymised (no customer or staff identity). Filter by sentiment, topic, time, location.
P3 | The Zeitgeist view | Single-page aggregate: NSS gauge + top 3 positive topics + top 3 concern topics + trend direction + recommended actions. | Not implemented | Design and build summary dashboard. This is what the business owner sees. Auto-generate recommended actions from data patterns.
P4 — Baseline Calibration (The Monday Morning Principle)
P4 | Daily measurement | Sentiment measured every day, every interaction. No sampling — full capture. | Not implemented | Configure pipeline for continuous capture. No sampling mode. Every interaction processed.
P4 | Individual daily baselines | System learns each person's weekly rhythm. Monday-them vs Wednesday-them vs Friday-them. Compare individuals to THEIR pattern on THAT day only. | Not implemented | Build individual baseline model. Accumulate per-person per-day-of-week averages over rolling 8-12 week window. Store as personal baseline profile.
P4 | Neutral day calibration | Identify and use most neutral day (likely Wed/Thu) as primary calibration anchor. Not Monday (flat), not Friday (buzzing). | Not implemented | Analyse variance across days of week. Statistically identify lowest-variance day per individual/team. Use as calibration reference point.
P4 | Monday morning noise filter | Monday morning sentiment dips acknowledged internally but NEVER surfaced to client. Never used for baseline. Never acted upon. | Not implemented | Build temporal filter. Flag Monday AM data as 'expected pattern — no action.' Exclude from alert triggers. Exclude from baseline calculation.
P4 | Signal vs noise classification | Distinguish baseline noise (Monday dips, Friday peaks, seasonal, weather) from actionable signals (multi-week deviations from individual patterns). | Not implemented | Define statistical thresholds for 'significant deviation' vs 'expected variation.' Require persistence across multiple days/weeks before classifying as signal. Build classifier.
P4 | Team pattern monitoring | Track when whole team's pattern shifts for 3+ weeks. This is signal, not noise. | Not implemented | Build team-level aggregation of individual baseline deviations. Alert when team-wide shift persists beyond threshold duration.
P5 — Staff Wellbeing Inference
P5 | Customer-to-staff correlation engine | When aggregate customer sentiment trends downward significantly and persistently, infer team-level wellbeing concern. | Not implemented | Build correlation model based on Service-Profit Chain framework. Define thresholds for 'significant' and 'persistent.' Test against historical data where available.
P5 | Team-level only output | All wellbeing indicators are team-level. Never individual. Physical enforcement — individual data aggregated before storage. | Not implemented | Design data schema that physically cannot store individual-level wellbeing indicators. Aggregation happens at write time, not query time. Audit schema.
P5 | Support-not-surveillance framing | All system outputs use supportive framing. 'Where might teams benefit from support?' Never accusatory. Never naming individuals. | Not implemented | Review and template all system-generated messages. Framing review by behavioural psychology lens. No negative language about individuals in any output.
P5 | Customer-centric messaging | All communications framed as 'this is all about customers.' Staff wellbeing inference is the mechanism, not the message. | Not implemented | Template all client-facing reports, dashboards, and notifications. Customer language only. Test messaging with focus group if possible.
P6 — Training-as-Support Delivery
P6 | Personal phone PWA | Mobile-first Progressive Web App for training delivery. Personal phone ONLY — no work device version exists. | Not implemented | Design and build PWA. Ensure no work-device compatibility (block corporate IP ranges, device fingerprinting). Four-word identifier as only access mechanism.
P6 | Four-word identifier system | Staff generate own anonymous identifier on personal device. No name, no employee number. System has no field for identity. | Not implemented | Build identifier generation (4 words from 5,000-word dictionary = 625 billion combinations). Local generation only. Database schema has NO name/ID fields. Physical enforcement.
P6 | Free training content curation | Curated free resources: YouTube, Khan Academy, OpenCourseWare, industry-specific microlearning. No cost to employer for content. | Not implemented | Build content curation pipeline. Source free, high-quality training resources. Categorise by topic, skill level, format. Adaptive matching to individual learner profile.
P6 | Adaptive learning engine | Training matched to individual pace, style, and language. System learns from engagement patterns. | Not implemented | Evaluate adaptive learning frameworks (OttoLearn, SC Training approach). Build or integrate adaptive engine. Personalise without storing identity.
P6 | Voluntary engagement model | Staff choose to engage or not. No tracking of completion. No consequence for declining. No follow-up if declined. | Not implemented | Design engagement model with zero tracking. No completion flags. No 'you haven't done your training' messages. Respect autonomy absolutely.
P6 | Supportive framing | 'That sounded like a really difficult time — do you want some training?' Never mandated, never tested, never assessed. A gift, not a syllabus. | Not implemented | Script all training offer messages. Test tone with behavioural psychology review. Ensure framing is warm, human, optional.
P7 — Positive Capture Loop (Celebration Engine)
P7 | Positive moment detection | System flags interactions scoring significantly above individual's baseline. Not just polite — genuinely delighted customer. | Not implemented | Define 'significantly above baseline' threshold. Build detection trigger in sentiment pipeline. Weight toward mid-week when genuine interactions are most likely.
P7 | Temporary on-device audio retention | For positive moments only: audio stays on-device in temporary buffer. 24-48 hour max. Auto-deleted if no consent. | Not implemented | Build separate audio buffer for positive captures. 48-hour TTL with hard auto-delete. On-device only — never transmitted without consent.
P7 | Staff celebration notification | Staff told 'You did something brilliant there' — celebration FIRST, before any content ask. | Not implemented | Design notification mechanism. Celebration message first. Replay clip if staff wants to hear. Only then ask about content use.
P7 | Dual consent chain | Staff asked permission then customer consent obtained or anonymised then staff chooses anonymous or named then AI writes story then staff checks then boss checks then published. | Not implemented | Build consent workflow. Staff consent first. Customer consent or anonymisation. Editorial chain: AI draft then staff review then manager review. Veto at any stage = immediate deletion.
P7 | Celebratory content creation | AI writes warm, human narrative. 'You should have heard Mrs. Smith. She was over the moon.' Never boastful. Staff and boss review before publish. | Not implemented | Build AI content generation for positive stories. Tone: celebratory, warm, specific. Template library for different content formats (social, newsletter, website). Review workflow.
P7 | Content publication | Published as authentic marketing — social media, website, newsletters. Genuine customer stories, not manufactured testimonials. | Not implemented | Build publication pipeline. Multi-format output. Attribution as per consent (anonymous or named). Archive for client's content library.
P8 — Transparency Inoculation (The Creepy Line)
P8 | Onboarding full disclosure | At onboarding: disclose EVERYTHING. Every capability, every data point, every process. No surprises. No phased disclosure. | Not implemented | Create comprehensive disclosure document (plain language, not legal). Walk new staff through every process. Offer independent advisor. Written documentation to take home.
P8 | Daily recording reminder | Every working day: remind staff recording is active. Not once at onboarding — every day. Normalisation through repetition. | Not implemented | Design daily reminder mechanism: indicator lights, brief audio cue, dashboard status. Subtle but consistent. Never skipped.
P8 | Early phase hands-off period | First 2-4 weeks: system accumulates baselines only. No interventions, no offers, no contact with new staff. | Not implemented | Build time-gated suppression of all intervention triggers for new staff. Let system learn their patterns before any interaction.
P8 | Graduated trust building | Weeks to months: begin offering timely, team-level support. Start with low-stakes, clearly beneficial offers. | Not implemented | Design trust-building progression. Start with general resources, move to more targeted support as relationship matures. Always team-level.
P8 | Team-level intervention framing | All support framed as team-level, circumstantial, never individual. 'Things have been busy lately' not 'you seemed stressed.' | Not implemented | Template all intervention messages. Review against creepy-line criteria. Test with staff panel if possible. No individual references ever.
P9 — Violence/Threat Exception
P9 | Automated threat detection | System detects threats of violence or actual violence in customer interactions. | Not implemented | Build threat detection model. Train on violent/threatening language patterns. Define detection threshold (high precision — false positives are harmful).
P9 | Immediate anonymised reporting | Detected threats immediately reported to police. Anonymised. No human intermediary holds identifiable data. | Not implemented | Build automated alert pipeline. Direct to emergency services or designated safety contact. Strip all personal identity before any human sees the alert.
P9 | Narrow scope enforcement | This is the ONLY exception to no-escalation. Scoped to physical danger only. Not rudeness, not frustration — violence/threats only. | Not implemented | Define scope narrowly in detection model. Document scope boundary. Regular review to prevent scope creep.
P10 — Kill Switch
P10 | CEO-accessible kill switch | Single action to disable entire system. Binary: on or off. No gradual wind-down. CEO or authorised person can activate. | Not implemented | Build kill switch mechanism. One button/command. Immediately stops all capture, analysis, and delivery. Purges all temporary buffers. System enters dormant state.
P10 | Immediate buffer purge | When kill switch activated, all temporary buffers (including positive capture) purged immediately. | Not implemented | Build purge routine triggered by kill switch. Verify complete deletion. Audit trail of kill switch activation (date/time/person only).
P10 | System dormancy state | After kill switch, system is fully dormant. No passive data collection. Can be reactivated only by same authority level. | Not implemented | Design dormancy state. Zero data flow. All pipeline components stopped. Reactivation requires same authorisation level as shutdown.
Rules — Non-Negotiable Rules
Rules | R1: Client data sovereignty | Customer voice data never leaves client infrastructure. Physical enforcement. | Not compliant — no system exists | Air-gap voice processing hardware. No cloud upload paths. Audit network routes. Penetration test.
Rules | R2: Audio retention policy | No raw audio retained except positive capture loop (24-48hr, consent-gated). | Not compliant — no system exists | Implement secure deletion pipeline. Positive capture buffer with hard 48hr TTL. Automated audit of deletion compliance.
Rules | R3: No staff voice from work devices | No microphone access on work systems. Hardware-level restriction. | Not compliant — no system exists | Hardware procurement spec: no microphone capability on work devices. Or OS-level mic access revocation. Audit device configuration.
Rules | R4: Personal phone only for training | No training application on work devices. No interface. No API endpoint. | Not compliant — no system exists | Build PWA for personal phone only. Block corporate IP ranges. Device fingerprinting to prevent work-device access.
Rules | R5: Four-word identifier only | Database has no field for name or employee ID. Cannot store identity. | Not compliant — no system exists | Database schema design: physically no columns for name, employee ID, email, or any PII. Schema-level enforcement.
Rules | R6: Aggregate before storage | Individual data aggregated at write time, not query time. Individual records do not exist post-aggregation. | Not compliant — no system exists | Design write pipeline: aggregate before INSERT. No individual-level table exists. Test that no query can return individual data.
Rules | R7: Violence exception | Automated detection then anonymised report then police. Only exception. | Not compliant — no system exists | Build detection model + anonymised alert pipeline. Narrow scope. Document legal basis (duty of care).
Rules | R8: Kill switch | Binary. CEO-accessible. One action. Immediate. | Not compliant — no system exists | Build kill switch. Test thoroughly. Document access control. Test purge completeness.
Rules | R9: Customer-centric framing | All communications use 'this is all about customers.' | Not compliant — no system exists | Template all client-facing and staff-facing language. Review all dashboards, reports, notifications. No staff-monitoring language anywhere.
Rules | R10: Support, not judgment | No negative framing about individuals in any system output. Ever. | Not compliant — no system exists | Review every system-generated message. Framing guidelines for all output. Automated scan for negative individual language.