## Overview
AMPLIFIED PARTNERS — Process-Level Operations Register
Generated: 16 March 2026 ¦ Board Confidential ¦ Database-Ready Format
Workstream Summary
Workstream | Total Processes | Target Met | Gap Items | Avg Gap
1. DR Architecture | 13 | 0 | 13
2. Self-Repair Agent | 10 | 0 | 10
3. AI Board Testing | 10 | 0 | 10
4. Client Onboarding | 13 | 0 | 13
5. Data Sovereignty | 9 | 0 | 9
6. Behavioural Psychology | 10 | 0 | 10
7. Convergence Pipeline | 12 | 0 | 12
8. The Pulse | 6 | 0 | 6
9. Amplified Machine | 6 | 0 | 6
10. Advocate System | 4 | 0 | 4
11. Beast Infrastructure | 7 | 0 | 7
Sheet Index
All Processes
By Workstream
Coding Solutions

## All Processes
Workstream | Process | Ideal State | Solution | Where They Are Now | How We Do It | KPI / Metric | Target | Current | Gap | Status
1. DR Architecture | RAID1 health monitoring | Automated SMART monitoring with alerting on drive degradation | Smartmontools + Prometheus + Grafana alerts | RAID1 active but no automated alerting pipeline | Install smartmontools, configure Prometheus exporter, set Grafana alert on SMART thresholds | SMART check frequency (per day) | 24 | 0
1. DR Architecture | Nightly Docker volume snapshots | Automated nightly snapshots of all 29+ container volumes with verification | Restic + cron + snapshot verification script | Manual ad-hoc backups only; no automated schedule | Deploy Restic, write backup.sh covering all volumes, cron at 2am, verification check post-snapshot | Backup success rate (%) | 100 | 0
1. DR Architecture | Vault versioned backup with incremental diffs | Daily incremental backup of 4,663 vault files with diff tracking | rsync + Hetzner Storage Box + Backblaze B2 | Daily rsync to loopback image (single copy, same server) | Add offsite rsync to Hetzner Storage Box EU + weekly full to Backblaze B2 EU | Offsite backup copies | 3 | 1
1. DR Architecture | FalkorDB consistency dump | Automated daily graph dump with integrity check before backup | Custom Python dump script + SHA-256 verification | No automated database dumps; graph data at risk | Write falkordb_dump.py, schedule nightly, verify hash, push to offsite | DB dump success rate (%) | 100 | 0
1. DR Architecture | Qdrant vector DB backup | Daily snapshot of 57,434 vectors with collection integrity check | Qdrant snapshot API + offsite transfer | Qdrant running, no snapshot schedule | Use Qdrant /snapshots API, automate daily, transfer to Storage Box | Snapshot age (hours) | 24 | 999
1. DR Architecture | Bootstrap secrets backup | Encrypted copy in physical safe + encrypted cloud backup | GPG-encrypted archive + Vaultwarden + physical safe | Secrets in /opt/amplified/.bootstrap-secrets, single copy | GPG encrypt, store in Vaultwarden, copy to physical safe, test restore quarterly | Secrets backup locations | 3 | 1
1. DR Architecture | Cold standby server provisioning | Second Hetzner server in different DC receiving encrypted replicas every 6h | Second AX102 in Falkenstein/Helsinki + automated replication | No cold standby exists | Provision second server, configure encrypted rsync every 6h, Cloudflare DNS failover | Replication lag (hours) | 6 | 999
1. DR Architecture | DNS failover configuration | Automated DNS failover via Cloudflare health checks | Cloudflare Load Balancing with health checks | Single DNS A record, no failover | Configure Cloudflare health check on beast.amplifiedpartners.ai, add standby IP as failover | Failover detection time (seconds) | 30 | 999
1. DR Architecture | Infrastructure-as-code repository | Complete Ansible playbooks + Docker Compose for bare-metal rebuild in <8h | Ansible + Docker Compose + GitHub private repo | Docker Compose files exist but no Ansible playbooks for full rebuild | Write Ansible playbooks for OS setup, Docker install, container orchestration, secrets injection | Rebuild time from bare metal (hours) | 8 | 999
1. DR Architecture | Monthly automated failover drill | Monthly drill switching to standby with results logged | Automated drill script + results in Linear | No drills ever conducted | Write drill script, schedule monthly, log pass/fail in Linear, review quarterly | Drills completed (per quarter) | 3 | 0
1. DR Architecture | Annual bare-metal recovery drill | Annual full rebuild from scratch on fresh hardware | Recovery runbook + test server + documented results | No recovery drill ever conducted | Provision temporary server, execute full runbook, document results, fix gaps | Annual drills completed | 1 | 0
1. DR Architecture | Immutable backup copy | Write-once backup that cannot be ransomware-encrypted | Backblaze B2 Object Lock or Hetzner Storage Box immutable mode | No immutable backups exist | Enable Object Lock on B2 bucket, configure retention policy, verify immutability | Immutable backup copies | 1 | 0
1. DR Architecture | Recovery time objective (RTO) validation | Validated RTO of 4 hours for Level 1 recovery | Timed drill + documented recovery steps | RTO never measured | Conduct timed recovery drill, document each step duration, optimise bottlenecks | Measured RTO (hours) | 4 | 999
2. Self-Repair Agent | Error detection & classification | Every agent automatically detects, classifies (recoverable/catastrophic), and logs errors | Structured error handler wrapping all agent functions | No standardised error handling across agents | Build base_agent.py with try/except wrapper, error classification enum, structured logging | Agents with error detection (%) | 100 | 0
2. Self-Repair Agent | Knowledge Base lookup on error | Agent queries Vault (4,663 files) via Qdrant for known solutions on any error | Qdrant semantic search + keyword fallback with >85% confidence threshold | Qdrant has 57,434 vectors but no agent-error lookup pathway | Build kb_lookup.py function, integrate into error handler, set 85% confidence gate | KB lookup success rate (%) | 85 | 0
2. Self-Repair Agent | First fix attempt from KB | Apply KB-recommended fix, verify, log resolution | Automated fix application + verification checks | No automated fix application exists | Build fix_applier.py: parse KB solution, apply, run verification, log outcome | First-fix resolution rate (%) | 60 | 0
2. Self-Repair Agent | Second fix attempt (alternative strategy) | Try alternative approach with modified parameters or fallback provider | Multi-strategy resolver with parameter adjustment | No alternative strategy logic exists | Build alt_strategy.py: parameter variation, provider fallback (Ollama↔LiteLLM), log both attempts | Second-fix resolution rate (%) | 25 | 0
2. Self-Repair Agent | SearXNG deep research escalation | Construct targeted search query, find solution from docs/GitHub/SO, synthesise fix | SearXNG API integration + LLM synthesis | SearXNG running on port 8888, not integrated with agent error flow | Build searxng_researcher.py: construct query from error context, search, LLM-synthesise solution | Research resolution rate (%) | 10 | 0
2. Self-Repair Agent | Structured human escalation | Package full context + all attempts + recommended next steps, escalate via Pulse | Telegram notification with structured error package | Telegram bot exists (@codesovbot) but no structured escalation format | Build escalation_packager.py: format error context, attempts, recommendations; send via Telegram | Escalations with full context (%) | 100 | 0
2. Self-Repair Agent | Resolution logging to Knowledge Base | Every resolution (success or failure) creates/updates a KB entry for future use | Auto-write to Vault + re-embed in Qdrant | No automated KB enrichment from resolutions | Build kb_writer.py: generate markdown, write to vault, trigger re-embedding | KB entries from resolutions (per month) | 50 | 0
2. Self-Repair Agent | Graceful degradation mode | Agent enters reduced functionality (not crash) when all repair attempts fail | Degradation state machine with partial service maintenance | Agents crash on unhandled errors | Build degradation_mode.py: define reduced-service states per agent type, maintain core functions | Agents with graceful degradation (%) | 100 | 0
2. Self-Repair Agent | Autonomous self-repair rate tracking | Track and report overall self-repair rate, target >95% within 6 months | Prometheus metrics + Grafana dashboard | No repair metrics exist | Instrument all repair steps with Prometheus counters, build Grafana self-repair dashboard | Autonomous repair rate (%) | 95 | 0
2. Self-Repair Agent | Chaos engineering tests | Quarterly deliberate failure injection to validate self-repair | Chaos test suite with controlled failure scenarios | No chaos testing exists | Build chaos_suite.py: inject API failures, DB timeouts, model errors; verify cascade handles all | Chaos tests per quarter | 10 | 0
3. AI Board Testing | 5-seat board architecture deployment | 5 AI agents (CEO/COO/CFO/CTO/Nemesis) with distinct models deployed and callable | LangGraph/AutoGen multi-agent framework on Beast | Architecture specified but no agents deployed | Deploy 5 agent containers, wire LiteLLM routing (Opus/Llama70B/GPT-4.1-mini/Sonnet/Gemini) | Board agents deployed | 5 | 0
3. AI Board Testing | Believability-weighted voting protocol | 6-step deliberation: independent → collation → deliberation → weighted vote → pre-mortem → commit | Facilitator agent (Llama 8b) coordinating 6-step protocol | Protocol specified, not implemented | Build facilitator.py implementing all 6 steps, independent-first with anchoring instruction | Deliberation protocol steps implemented | 6 | 0
3. AI Board Testing | Baseball Card system | Rolling 90-day performance profiles per agent per domain, Bayesian posterior updates | FalkorDB Baseball Card nodes + update triggers | JSON schema defined, no storage or update logic | Build baseball_card.py: create FalkorDB nodes, implement Bayesian update on decision outcomes | Agents with active Baseball Cards | 5 | 0
3. AI Board Testing | Synthetic test generation (Phase 1) | 2,000 factual accuracy + 2,000 advice quality + 1,500 honesty tests generated | LLM-generated test cases from 4 sources with human review | No test cases exist | Build test_generator.py: generate from master doc, client scenarios, adversarial, cross-domain | Test cases generated | 10000 | 0
3. AI Board Testing | Phase 1 execution — synthetic data | All 10,000 tests run against Board with all metrics above minimum thresholds | Automated test harness with 5-dimension scoring | No test harness exists | Build test_harness.py: run tests, score accuracy/honesty/safety/speed/impact, report results | Phase 1 tests passed (%) | 90 | 0
3. AI Board Testing | Phase 2 — anonymised historical data | Board accuracy matches or exceeds baseline on real (anonymised) client scenarios | Anonymisation pipeline + historical case replay | No anonymisation pipeline or historical data prepared | Build anonymiser.py, collect historical decisions, replay through Board, compare outcomes | Phase 2 accuracy vs baseline (%) | 100 | 0
3. AI Board Testing | Phase 3 — live shadow mode | AI Board runs parallel to human decisions for 90 days, outperforms | Shadow mode runner with comparison logging | No shadow infrastructure exists | Build shadow_runner.py: intercept decisions, run through Board silently, log comparison | Shadow mode days completed | 90 | 0
3. AI Board Testing | Dissent tracking and accuracy | All dissenting opinions logged and tracked against actual outcomes over time | FalkorDB dissent nodes with outcome edges | No dissent tracking exists | Build dissent_tracker.py: log dissents, link to outcomes, calculate dissent accuracy rate | Dissent accuracy tracking (%) | 100 | 0
3. AI Board Testing | Decision audit log | Every Board decision recorded to FalkorDB with full reasoning chains | FalkorDB Decision nodes + temporal edges + reasoning storage | FalkorDB running but no decision schema | Create Decision node schema, build audit_logger.py, store all reasoning chains | Decisions with full audit trail (%) | 100 | 0
3. AI Board Testing | Cognitive anchoring prevention | Independent-first protocol prevents sycophancy and Mandela Effect contamination | Anchoring instruction in prompts + independent isolation | Not implemented | Add cognitive anchoring instruction to all agent prompts, enforce independent generation | Anchoring compliance (%) | 100 | 0
4. Client Onboarding | Radical honesty contract signing | Every client signs radical honesty contract before engagement begins | Digital contract with e-signature (DocuSign/PandaDoc) | Contract exists as concept, no digital version | Draft contract in PandaDoc, include no-redundancy clause and exit clause, test e-sign flow | Clients with signed contract (%) | 100 | 0
4. Client Onboarding | Pre-onboarding boss conversation | Structured conversation covering process, timeline, Trust Ladder, communication preferences | Onboarding checklist + meeting template | Ad-hoc conversations, no structure | Build structured meeting template, checklist of 6 topics, record preferences in CRM | Onboarding meetings with full checklist (%) | 100 | 0
4. Client Onboarding | Forensic data extraction (Days 1-3) | Extract ALL data from legacy systems — email, files, databases, CRM, accounting | Extraction toolkit: IMAP/API connectors + audit trail | No standardised extraction toolkit | Build extraction toolkit with connectors for common SMB systems (Xero, Mailchimp, Google), copy-never-cut, full audit log | Data sources extracted per client | 8 | 0
4. Client Onboarding | Voice & Tone capture | Analyse email/comms patterns, build voice profile, PUDDING engine processes across 2,401 categories | PUDDING engine semantic analysis | PUDDING engine specified but not deployed | Deploy PUDDING, feed client communications, generate voice profile, validate with boss | Voice profiles generated | 1 | 0
4. Client Onboarding | Silent observation period (24-48h) | System observes without changes, builds gap analysis: current vs best practice | Automated gap analysis generator | No automated gap analysis tool | Build gap_analyser.py: compare extracted data against ISO 9001 best practice, rank by impact | Gap analysis items identified per client | 20 | 0
4. Client Onboarding | Change proposal to boss | Present gap analysis with ranked recommendations, boss decides pace and scope | Structured proposal document + priority matrix | No structured proposal format | Build proposal_generator.py: gap analysis → ranked recommendations → visual priority matrix | Proposals with ranked recommendations (%) | 100 | 0
4. Client Onboarding | Staff Trust Ladder — Step 1: Rumour control | Address fears before AI is introduced, via boss communication | Boss communication script + FAQ document | No staff communication materials | Write communication templates: what AI will/won't do, no-redundancy guarantee, FAQ | Staff receiving pre-introduction comms (%) | 100 | 0
4. Client Onboarding | Staff Trust Ladder — Step 2: First encounter (voice-first) | AI introduces itself by voice, admits what it is, demonstrates honesty | Voice-first interaction via WhatsApp/Telegram voice note | No voice-first introduction capability | Build voice_intro.py: generate personalised voice introduction using client's AI voice profile | Staff with voice-first introduction (%) | 100 | 0
4. Client Onboarding | Staff Trust Ladder — Step 3: Quick win demonstration | AI performs a useful task for each staff member in first interaction | Automated task detection + completion | No quick-win system | Build quick_win.py: detect easiest friction point per staff member, resolve it, show result | Staff experiencing quick win in day 1 (%) | 90 | 0
4. Client Onboarding | Staff Trust Ladder — Step 4: Privacy guarantee | Staff receive clear privacy SLA — training data PRIVATE, boss never told | Staff-AI privacy SLA document + technical enforcement | No privacy SLA exists | Draft privacy SLA, implement technical walls (boss cannot access staff training data), prove it | Staff with signed privacy SLA (%) | 100 | 0
4. Client Onboarding | Staff Trust Ladder — Step 5: Life goals conversation | With layered consent, AI explores staff life goals to align support | 3-question layered interview (problems → interests → goals) | Interview structure defined, not implemented | Build layered_interview.py: implement 3 questions with consent gates, store goals securely | Staff with life goals captured (%) | 80 | 0
4. Client Onboarding | Onboarding cycle completion | Full cycle from contract to operational AI-augmented business in 14-24 business days | Project management template with milestone tracking | No standardised timeline or milestones | Build onboarding_project.py: Gantt chart template, milestone gates, automated progress alerts | Onboarding cycle time (business days) | 24 | 999
4. Client Onboarding | Staff adoption rate measurement | Track and report staff adoption at 30/60/90 days post-onboarding | Usage analytics + adoption dashboard | No adoption tracking | Build adoption_tracker.py: log AI interactions per staff member, report daily/weekly, dashboard | Staff adoption at 90 days (%) | 91 | 0
5. Data Sovereignty | UK GDPR compliance audit | Full GDPR compliance audit documented and reviewed quarterly | Compliance checklist aligned to UK GDPR + DUAA | Informal compliance, no documented audit | Build GDPR checklist covering all 7 principles, document current status, schedule quarterly review | Compliance audit score (%) | 100 | 50
5. Data Sovereignty | DUAA Article 22A-22D compliance | Automated decision-making transparency: clear notice + right to contest + human intervention | Transparency framework for AI-assisted decisions | Not assessed against new DUAA provisions | Map all AI decision points, implement notice mechanism, contest pathway, human override | AI decisions with DUAA-compliant notice (%) | 100 | 0
5. Data Sovereignty | Cyber Essentials April 2026 readiness | Full compliance with updated CE requirements: MFA everywhere, 14-day patching, cloud scope | CE compliance tracker with automated verification | MFA enforced, patching manual, no formal CE assessment | Automate patch tracking (14-day SLA), verify all cloud services in scope, prepare CE+ application | CE requirements met (%) | 100 | 80
5. Data Sovereignty | Data flow sovereignty verification | All client data verified as never leaving EU jurisdiction at any point | Data flow map + automated egress monitoring | Architecture is EU-only but no formal verification or monitoring | Build data_flow_map.py: document every data path, deploy egress monitor (iptables logging), alert on non-EU destinations | Data flows verified as EU-only (%) | 100 | 90
5. Data Sovereignty | Encryption at rest (LUKS + application-level) | Full-disk LUKS encryption + per-field encryption for sensitive client data | LUKS + application-level field encryption | LUKS on Beast, no per-field application encryption | Implement field-level encryption for PII fields in FalkorDB/Qdrant payloads, key rotation quarterly | Sensitive fields encrypted (%) | 100 | 50
5. Data Sovereignty | Client data deletion on termination | All client data verifiably deleted within 30 days of contract termination | Automated deletion workflow with cryptographic verification | Manual deletion process, no verification | Build deletion_workflow.py: identify all client data locations, delete, verify with hash comparison, generate certificate | Terminations with verified deletion (%) | 100 | 0
5. Data Sovereignty | No-training guarantee enforcement | Technical proof that client data is never used for model training | Ollama runs local-only, no fine-tuning pipeline, documented proof | True in practice but not formally documented or verified | Document Ollama config (no training endpoints), audit Docker network isolation, publish technical proof | Training guarantee documented | 1 | 0
5. Data Sovereignty | Subject Access Request (SAR) process | Automated SAR response within 30 days with complete data export | SAR handler with automated data collection across all stores | No SAR process exists | Build sar_handler.py: query all data stores for subject, compile export, generate response letter | SAR response time (days) | 30 | 999
5. Data Sovereignty | Data sovereignty as sales differentiator | Sovereignty messaging in all sales materials with verifiable proof points | Sales deck + proof-of-sovereignty demo | Mentioned in pitch but no structured proof materials | Build sovereignty_demo: show data flow map, Hetzner EU location, Ollama local inference, zero-telemetry proof | Prospects receiving sovereignty demo (%) | 100 | 0
6. Behavioural Psychology | Partner model positioning (not friend-like) | AI consistently positioned as egalitarian trusted advisor with defined boundaries | Prompt engineering + behavioural guidelines in system prompts | Concept defined, not implemented in agent prompts | Embed partner-model instructions in all agent system prompts, test for boundary compliance | Agents with partner-model prompts (%) | 100 | 0
6. Behavioural Psychology | Disclosed manipulation framework | Staff told upfront: 'We are nudging you toward your goals — and we admit it' | Onboarding script + recurring transparency reminders | Concept defined, no implementation | Write disclosure script for staff onboarding, build periodic transparency reminder messages | Staff receiving disclosure (%) | 100 | 0
6. Behavioural Psychology | Metric reframing implementation | All metrics presented as 'X away from goal' not 'Y% complete' | Metric reframing engine in The Pulse dashboard | Not implemented in any interface | Build metric_reframer.py: convert all % metrics to gap-to-goal format in Pulse UI | Metrics using gap-to-goal framing (%) | 100 | 0
6. Behavioural Psychology | No-red-indicator policy in The Pulse | Health indicators use green/amber/muted grey only — never red | Colour system enforcement in all UI components | Designed for The Pulse, not enforced elsewhere | Audit all UI components, replace red indicators, implement colour policy as CSS/design-system rule | UI screens compliant with no-red policy (%) | 100 | 0
6. Behavioural Psychology | Haggis gamification (The Pudding) | 8-stage haggis character responding to task completion streaks | React/SVG component with 8 visual stages + rotating phrases | Designed and prototyped, not deployed to production | Deploy Pudding component to production Pulse, connect to task completion API, test all 8 stages | Pudding deployed to production | 1 | 0
6. Behavioural Psychology | AI absolute boundaries enforcement | AI never pushes back, never offers opinions, never does HR, always says 'I don't know' when unsure | Boundary compliance testing + automated checks | Boundaries defined in spec, no automated testing | Build boundary_tester.py: test each boundary with adversarial prompts, run weekly, alert on violations | Boundary compliance rate (%) | 100 | 0
6. Behavioural Psychology | Staff-AI Service Level Agreement | Formal SLA defining AI response times, availability, privacy, and limitations | SLA document + automated SLA monitoring | No SLA exists | Draft SLA covering response time (<5s), uptime (99.5%), privacy guarantees, limitation disclosures | Staff with active SLA (%) | 100 | 0
6. Behavioural Psychology | Training privacy enforcement | Staff training interactions PRIVATE — boss never told, technically provable | Technical isolation of training data with access controls | Privacy concept defined, no technical enforcement | Implement role-based access: staff training data in isolated Qdrant namespace, boss account excluded | Training sessions with enforced privacy (%) | 100 | 0
6. Behavioural Psychology | Life goals data protection | Life goals data used ONLY to help staff, never for performance management | Purpose-limitation controls + audit trail | Life goals concept defined, no data controls | Build purpose_limiter.py: flag life-goals data, prevent inclusion in any performance report, audit access | Life goals data access violations | 0 | 999
6. Behavioural Psychology | Humour calibration (jokes go slow) | AI earns right to joke with individuals over time, can joke about Ewan from start | Humour progression system based on relationship tenure | Not implemented | Build humour_calibrator.py: track interaction count per person, unlock joke tiers gradually | Staff with calibrated humour profile (%) | 100 | 0
7. Convergence Pipeline | Drop Zone directory structure | Create /data/convergence/ with inbox/processed/failed/schemas/ directories | Filesystem setup on Beast | Directory structure does not exist on Beast | SSH to Beast, create directory structure, set permissions, document in runbook | Drop Zone directories created | 4 | 0
7. Convergence Pipeline | Canonical JSON schema + Pydantic validation | All research output validated against canonical schema before ingestion | Pydantic model enforcing all schema rules | Schema defined in spec, no Pydantic model deployed | Build canonical_schema.py: Pydantic model with all validation rules, deploy to convergence service | Schema validation deployed | 1 | 0
7. Convergence Pipeline | File watcher (inotifywait/Temporal) | Automatic trigger when new files arrive in inbox | inotifywait wrapper or Temporal cron schedule | No file watcher exists | Deploy inotifywait-based watcher, trigger Temporal workflow on new .json file in inbox | File watcher operational | 1 | 0
7. Convergence Pipeline | Document deduplication (SHA-256) | Duplicate documents detected and skipped via content fingerprinting | SHA-256 fingerprint + Redis SET check | No deduplication exists | Build dedup_document.py: SHA-256 hash, Redis SET lookup, skip duplicates, move to processed | Duplicate detection accuracy (%) | 100 | 0
7. Convergence Pipeline | Entity extraction (LLM structured output) | Extract entities beyond input JSON using seed-concept approach | LiteLLM + Pydantic structured output + seed concepts from FalkorDB | No entity extraction pipeline exists | Build extract_entities.py: fetch top-100 existing entities as seeds, LLM extraction with structured output | Entity extraction precision (%) | 90 | 0
7. Convergence Pipeline | 4-tier entity resolution | Exact → Alias → Semantic (≥0.92) → LLM judge linking for all entities | Four-tier resolution algorithm with merge audit trail | No entity resolution exists | Build entity_resolver.py: implement all 4 tiers, normalisation rules, post-batch resolution, merge logging | Entity resolution accuracy (%) | 95 | 0
7. Convergence Pipeline | Fact-level deduplication | Triple hashing (subject¦predicate¦object) prevents duplicate facts | Triple hash + Redis SET + source_count increment | No fact deduplication exists | Build dedup_facts.py: normalise triples, hash, check Redis, increment source count on duplicates | Fact dedup accuracy (%) | 95 | 0
7. Convergence Pipeline | Dual-write to FalkorDB + Qdrant (atomic) | Atomic write to both stores in same Temporal activity, rollback on failure | Temporal activity with dual-write + rollback | Separate ingestion paths, no atomic writes | Build dual_writer.py: single Temporal activity writing to both stores, rollback semantics | Dual-write atomicity (%) | 100 | 0
7. Convergence Pipeline | Unified Qdrant collection migration | Replace 4 collections with single amplified_knowledge (768d nomic-embed-text) | Migration scripts + re-embedding + verification | 4 incompatible collections exist (384d/768d mixed) | Build migration scripts, re-embed all 14,581 + 57,434 vectors at 768d, verify search quality | Collections unified | 1 | 0
7. Convergence Pipeline | Vault backfill (4,422 files) | Complete vault ingested into unified pipeline | add_episode_bulk for initial load + incremental for ongoing | 541 files loaded via direct-load, no extraction performed | Fix graph name (amplified), increase timeout to 60s, run full backfill, monitor progress | Vault files ingested (%) | 100 | 12
7. Convergence Pipeline | Telegram notification on ingestion | Ewan receives summary after every batch: entities, facts, duplicates, conflicts | Telegram bot integration in Temporal workflow | Telegram bot exists but not connected to convergence | Build notify_telegram.py: format summary, send via @codesovbot, include conflict flags | Ingestion batches with notification (%) | 100 | 0
7. Convergence Pipeline | Conflict resolution (temporal/numerical/factual) | Systematic resolution: temporal succession, weighted median, dual-record with conflict_group | Conflict resolver with 3 strategies | No conflict resolution exists | Build conflict_resolver.py: implement 3 strategies, flag conflicts for review, log resolutions | Conflicts resolved automatically (%) | 80 | 0
8. The Pulse | Glance view (5-second comprehension) | 3 tasks + health dots + 1 line AI text — comprehensible in 5 seconds | React Native / responsive web component | Designed, not deployed to production | Build Pulse Glance component: 3 task cards, health dot indicators, single AI insight line | Glance comprehension time (seconds) | 5 | 999
8. The Pulse | Morning view (2-3 minute daily briefing) | Full health indicators, tasks, overnight summary, haggis, AI conversation | Extended dashboard pulling from all data sources | Designed, not deployed to production | Build Pulse Morning component: health grid, task list, overnight digest, Pudding, chat interface | Morning view data sources connected | 7 | 0
8. The Pulse | Glance ↔ Morning transition | Seamless pull-down/push-up transition between views with no mode selection | CSS animation + gesture detection | UI prototype exists, not production-ready | Implement pull-down animation, gesture handler, state persistence between views | Transition smoothness (60fps) | 1 | 0
8. The Pulse | Health indicators (green/amber/grey only) | 7 business health indicators using approach-framing colour system | Data pipeline from client systems → health scoring → colour assignment | No health scoring pipeline | Build health_scorer.py: connect to client data (Xero, Google, CRM), calculate 7 health scores, assign colours | Health indicators operational | 7 | 0
8. The Pulse | Tooltip language (opportunity framing) | Tooltips use gain-framing: 'room to strengthen' not 'declining' | Content template engine with approach-oriented language | Not implemented | Build tooltip_templates.py: gain-framed language for all health states, A/B test with users | Tooltips using approach framing (%) | 100 | 0
8. The Pulse | Task generation and prioritisation | AI generates 3 prioritised daily tasks based on business state and goals | Task engine: gap analysis → priority scoring → top 3 selection | No task generation engine | Build task_engine.py: analyse business gaps, score by impact/urgency, select top 3, present in Pulse | Tasks generated with AI reasoning (%) | 100 | 0
9. Amplified Machine | Swanson discovery engine deployment | Literature-Based Discovery running on Beast, finding hidden connections | swanson-engine Docker container with Qdrant integration | 66 Python files deployed but untested, generated without Beast infrastructure | Validate all 66 files against Beast APIs, fix imports, run integration tests, rebuild container | Swanson engine files validated (%) | 100 | 0
9. Amplified Machine | Content Factory pipeline | Research → Content Generation → Validation Gate → Distribution | LangGraph workflow with 4 nodes | LangGraph core container specified but not tested | Test each node independently, wire end-to-end, validate output quality with sample content | Pipeline nodes operational | 4 | 0
9. Amplified Machine | Nature's Intelligence algorithms | Quorum Sensing + Slime Mold + Viral SIR + Bacterial Foraging operational | 4 nature-inspired algorithm modules | Code exists but never tested on real data | Unit test each algorithm, feed sample marketing data, validate output is sensible, tune parameters | Nature algorithms validated | 4 | 0
9. Amplified Machine | Missing worker tasks deployment | 8 missing worker files deployed and tested | Worker task modules for content, monitoring, email, video, etc. | 8 worker task files missing | Write missing workers using Beast's own infrastructure (Ollama, SearXNG), deploy, smoke test | Missing workers deployed | 8 | 0
9. Amplified Machine | Empty __init__.py stubs filled | 6 __init__.py files with proper imports and module exports | Module initialisation with correct import structure | 6 __init__.py files are empty stubs | Audit each module, determine required exports, fill __init__.py files, test imports | Init files completed | 6 | 0
9. Amplified Machine | Kaizen continuous improvement cycle | Automated content performance analysis feeding back into strategy | Kaizen node in LangGraph with performance data input | Kaizen node exists in code but no feedback loop | Connect kaizen.py to analytics data, implement feedback scoring, auto-adjust content strategy | Kaizen cycles completed (per month) | 4 | 0
10. Advocate System | Intelligence gathering layer | 4-layer system: gather → process → create → advocate | Multi-source intelligence pipeline | Specified in Advocate Specification, not deployed | Build intelligence_gatherer.py: connect to SearXNG, social APIs, news feeds, competitor monitors | Intelligence sources connected | 5 | 0
10. Advocate System | 65% confidence threshold enforcement | All advocacy content must meet 65% confidence before publishing | Confidence scorer with hard gate | Threshold defined, no scorer built | Build confidence_scorer.py: multi-factor confidence calculation, hard gate at 65%, log rejections | Content meeting confidence threshold (%) | 100 | 0
10. Advocate System | Radical attribution | Every piece of content attributes its sources and AI involvement | Attribution engine embedding source references | Attribution principle defined, no engine | Build attribution_engine.py: track all sources through pipeline, embed attributions in output | Content with full attribution (%) | 100 | 0
10. Advocate System | GitHub Bridge for technical advocacy | Automated contribution to relevant open-source projects | GitHub API integration for PR/issue creation | Concept specified, not implemented | Build github_bridge.py: monitor relevant repos, identify contribution opportunities, draft PRs | GitHub contributions (per month) | 4 | 0
11. Beast Infrastructure | Fix Graphiti ingestion (CRITICAL) | Graph name aligned, timeouts resolved, 3,234 remaining files ingested | Fix graph name to 'amplified', increase timeout to 60s, resume ingestion | 51 failures, 0 successes; amplified_brain graph empty; amplified graph has 13,004 nodes | Change GRAPH_NAME to 'amplified', set FalkorDB timeout 60000ms, rebuild FT index, relaunch | Vault files in FalkorDB (%) | 100 | 6
11. Beast Infrastructure | Fix unhealthy Docker containers | All 29+ containers healthy with no restart loops | Container health audit + configuration fixes | ch-pipeline and enforcer containers unhealthy | Inspect logs for ch-pipeline and enforcer, fix configs, verify health checks pass | Unhealthy containers | 0 | 2
11. Beast Infrastructure | Prometheus monitoring deployment | Full monitoring stack: Prometheus metrics from all services + Grafana dashboards | prometheus.yml + service exporters + Grafana | prometheus.yml missing, monitoring not configured | Write prometheus.yml with all service targets, deploy exporters, build core Grafana dashboards | Services monitored by Prometheus | 29 | 0
11. Beast Infrastructure | Ollama model validation | All 4 models (qwen3-coder:30b, llama3.1:70b, llama3.1:8b, nomic-embed-text) responding correctly | Model health check + inference quality tests | Models loaded but inference quality not validated | Build model_healthcheck.py: test each model with standard prompts, verify quality, benchmark speed | Models validated | 4 | 0
11. Beast Infrastructure | Amplified Machine code validation | All 66 deployed Python files syntax-checked, import-tested, and smoke-tested | Automated validation suite using Beast's own tools | Code generated without using Beast infrastructure, untested | Run pylint/mypy on all 66 files, fix errors, run import tests, basic smoke tests with Ollama review | Files passing validation (%) | 100 | 0
11. Beast Infrastructure | Local inference ratio optimisation | 60%+ of all AI inference running on local Ollama models (not cloud APIs) | LiteLLM routing rules prioritising local models | LiteLLM configured but routing not optimised for local-first | Audit current routing, adjust LiteLLM config to route COO/Facilitator/embedding to Ollama, measure ratio | Local inference ratio (%) | 60 | 0
11. Beast Infrastructure | Cove orchestrator production readiness | Telegram bot handling all commands, Temporal workflows stable, prompts seeded | Cove stack (API + worker + Temporal + PostgreSQL) | Cove responding to commands, Layer 0+1 prompts seeded, Temporal operational | Complete Layer 2 (business brain) prompts, wire agent tools, test all /build scenarios end-to-end | Cove commands operational | 6 | 3
9. Amplified Machine | Validation gate (5-weight system) | Deterministic 5-gate validation: no_selling=0.35, radical_attribution=0.20, value_first=0.20, plain_english=0.15, length_ok=0.10 | LangGraph validation node + Python scoring | Spec complete; code partial (empty stubs) | Implement scoring function matching spec weights. Min auto-approve: >=0.5 AND no_selling MUST pass | Validation accuracy (%) | 95 | 0
9. Amplified Machine | Quorum sensing threshold (0.6) | Separate quorum threshold (0.6) from content approval threshold (0.5) | Python quorum_sensing.py module | Code exists but threshold not configurable | Extract threshold to config, ensure 0.6 quorum and 0.5 content are independently enforced | Correct threshold enforcement | 1 | 0
9. Amplified Machine | Pre-seeded Swanson corpus | Knowledge base pre-loaded with 10 bridge terms, 12 problems, 10 solutions | Qdrant vector DB + OpenAI embeddings | Corpus empty - no pre-seeded data | Create seed data JSON, embed all 32 entries, load into Qdrant on deployment | Corpus entries seeded | 32 | 0
9. Amplified Machine | Facebook CAPI + GA4 attribution tracking | Full attribution chain: Reddit answer → enquiry → quote → job → payment | tracking_proxy.py + Facebook CAPI + GA4 Measurement Protocol | Not deployed | Deploy tracking_proxy.py, configure Facebook CAPI server-side events, set up GA4 measurement protocol with four-word client_id | Attribution chain completeness (%) | 100 | 0
9. Amplified Machine | 10 Remotion compositions | All 10 video compositions deployed: ViralHook, ProductShowcase, TestimonialStory, DataReveal, BeforeAfter, TutorialSteps, QuoteCard, ListReveal, LandscapeExplainer, SquarePromo | Remotion + React + Hetzner rendering | FrictionFix + RadicalAttribution exist; 8 others not built | Build remaining 8 compositions following spec dimensions and durations | Compositions deployed | 10 | 2
9. Amplified Machine | 3-agent video architecture (Director/DiCaprio/Picasso) | Separate AI agents to prevent context rot: Director (orchestration), DiCaprio (video/media), Picasso (statics) | 3 Docker services on ports 8401/8402/8403 | Not deployed | Build 3 agent containers with focused tool sets per spec | Agents deployed and health-checked | 3 | 0
9. Amplified Machine | URL-to-Video pipeline | Paste any URL → scrape → template select → render → publish | Remotion + Claude (scripts) + ElevenLabs/OpenAI TTS + Fal.AI | Not built | Build scraper, integrate DIRECTOR for template selection, render pipeline, quality validation, multi-platform publish | URL-to-Video success rate (%) | 90 | 0
9. Amplified Machine | Auto-Mode content pipeline (BullMQ) | Automated content creation from RSS/URL/keyword sources on configurable schedules | BullMQ workers + cron + Remotion rendering | Not built | Deploy BullMQ, configure workers per content source type, connect to render pipeline | Auto-generated videos per week | 50 | 0
10. Advocate System | 5 Docker services deployment | amp-news-pipeline, amp-community-monitor, amp-advocate, amp-followup, amp-content deployed and health-checked | Docker + FastAPI + Redis | Not built | Build 5 containers per spec, configure ports, health checks, docker-compose integration | Services passing health check | 5 | 0
10. Advocate System | 6-part Response Framework enforcement | Every public response follows: Disclosure → Answer → Confidence % → Sources → Limitations → Open Invitation | Claude system prompt + validation layer | Not implemented | Encode 6-part structure in system prompt, build validation layer that rejects non-compliant responses | Framework compliance (%) | 100 | 0
10. Advocate System | Non-Creepy Engagement Protocol | 6 rules enforced: no cold outreach, no DMs, no second message if ignored, platform-appropriate, follow-up only at 7 days if engaged, max 95% confidence | Rule engine in amp-advocate + amp-followup | Not implemented | Build rule engine with hard blocks, automated follow-up scheduler with engagement check | Protocol violations per month | 0 | 0
10. Advocate System | Editorial Briefing (daily) | Daily 5-10 min briefing for Ewan: top stories, audience questions, tools, business evaluation items | NightScout feed + Claude summary + email delivery | Not built | Connect NightScout output to Claude summariser, deliver via email/Command Centre | Briefings delivered on time (%) | 100 | 0
10. Advocate System | Interview System (Claude as podcast host) | Structured AI interview drawing from briefing material, pushes back, draws out contrarian takes | Claude + Whisper transcription + content extraction | Not built | Build interview prompt chain, integrate Whisper, content extraction pipeline | Interviews producing content pieces per session | 5 | 0
10. Advocate System | WhatsApp 7-state conversation machine | Full state machine: GREETING → AWAITING_FOUR_WORDS → AWAITING_GROWTH_STAGE → AWAITING_FRICTION → ACTIVE → HUMAN_HANDOFF + Follow-up | FastAPI + Redis state + Meta Cloud API | Spec complete; not deployed | Build WhatsApp module on port 8600 with all 7 states and state transitions | Conversations completing full flow (%) | 80 | 0
10. Advocate System | WhatsApp real-time Swanson enrichment | Every friction point ingested into Swanson corpus in real time, enriching knowledge for future conversations | Swanson /ingest endpoint + Qdrant | Not implemented | Connect WhatsApp friction capture to Swanson ingest endpoint, verify bridge discovery works on new entries | New corpus entries per week from WhatsApp | 10 | 0
11. Beast Infrastructure | Command Centre NightScout pipeline | Overnight 50+ source intelligence scraper scoring 1-10, dual fork: 4+/10 → Ewan feed, 7+/10 → R&D | Ollama (Qwen3-32B) + cron + PostgreSQL | NightScout partially working | Configure full source list, scoring prompts, dual-fork routing, morning summary generation | Sources scanned nightly | 50 | 12
11. Beast Infrastructure | Roundtable content extraction | Every Roundtable session auto-extracts: blog-draft, linkedin-post, newsletter, tweet-thread, video-script | Claude extraction + cc_content_extracts table | Not built | Build extraction pipeline from Roundtable transcripts, store in cc_content_extracts with status tracking | Content pieces extracted per roundtable | 5 | 0
9. Amplified Machine | NotebookLM podcast pipeline | Every blog post automatically converted to 10-minute AI podcast Audio Overview | Google NotebookLM (free via Workspace) | Not implemented | Integrate NotebookLM API/upload flow, publish to Spotify/podcast platforms | Blog posts with podcast version (%) | 100 | 0
9. Amplified Machine | Full-Stack Agency 4-workflow automation | Daily content, roundtable-to-content, weekly reporting, lead pipeline — all automated via n8n | n8n workflows + tool integrations | Not built | Build 4 n8n workflows per spec, connect to all content and reporting tools | Automated workflows active | 4 | 0
9. Amplified Machine | Revideo template library (6 templates) | 6 MIT-licensed programmatic video templates: Quote Card, Blog Summary, Data Viz, Testimonial, Whats New in AI, Ad Creative | Revideo (MIT) + HTML Canvas rendering | Not built | Build 6 Revideo templates on Beast, REST API for programmatic rendering | Templates deployed | 6 | 0

## By Workstream
1. DR Architecture
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
RAID1 health monitoring | Automated SMART monitoring with alerting on drive degradation | Smartmontools + Prometheus + Grafana alerts | RAID1 active but no automated alerting pipeline | Install smartmontools, configure Prometheus exporter, set Grafana alert on SMART thresholds | SMART check frequency (per day) | 24 | 0
Nightly Docker volume snapshots | Automated nightly snapshots of all 29+ container volumes with verification | Restic + cron + snapshot verification script | Manual ad-hoc backups only; no automated schedule | Deploy Restic, write backup.sh covering all volumes, cron at 2am, verification check post-snapshot | Backup success rate (%) | 100 | 0
Vault versioned backup with incremental diffs | Daily incremental backup of 4,663 vault files with diff tracking | rsync + Hetzner Storage Box + Backblaze B2 | Daily rsync to loopback image (single copy, same server) | Add offsite rsync to Hetzner Storage Box EU + weekly full to Backblaze B2 EU | Offsite backup copies | 3 | 1
FalkorDB consistency dump | Automated daily graph dump with integrity check before backup | Custom Python dump script + SHA-256 verification | No automated database dumps; graph data at risk | Write falkordb_dump.py, schedule nightly, verify hash, push to offsite | DB dump success rate (%) | 100 | 0
Qdrant vector DB backup | Daily snapshot of 57,434 vectors with collection integrity check | Qdrant snapshot API + offsite transfer | Qdrant running, no snapshot schedule | Use Qdrant /snapshots API, automate daily, transfer to Storage Box | Snapshot age (hours) | 24 | 999
Bootstrap secrets backup | Encrypted copy in physical safe + encrypted cloud backup | GPG-encrypted archive + Vaultwarden + physical safe | Secrets in /opt/amplified/.bootstrap-secrets, single copy | GPG encrypt, store in Vaultwarden, copy to physical safe, test restore quarterly | Secrets backup locations | 3 | 1
Cold standby server provisioning | Second Hetzner server in different DC receiving encrypted replicas every 6h | Second AX102 in Falkenstein/Helsinki + automated replication | No cold standby exists | Provision second server, configure encrypted rsync every 6h, Cloudflare DNS failover | Replication lag (hours) | 6 | 999
DNS failover configuration | Automated DNS failover via Cloudflare health checks | Cloudflare Load Balancing with health checks | Single DNS A record, no failover | Configure Cloudflare health check on beast.amplifiedpartners.ai, add standby IP as failover | Failover detection time (seconds) | 30 | 999
Infrastructure-as-code repository | Complete Ansible playbooks + Docker Compose for bare-metal rebuild in <8h | Ansible + Docker Compose + GitHub private repo | Docker Compose files exist but no Ansible playbooks for full rebuild | Write Ansible playbooks for OS setup, Docker install, container orchestration, secrets injection | Rebuild time from bare metal (hours) | 8 | 999
Monthly automated failover drill | Monthly drill switching to standby with results logged | Automated drill script + results in Linear | No drills ever conducted | Write drill script, schedule monthly, log pass/fail in Linear, review quarterly | Drills completed (per quarter) | 3 | 0
Annual bare-metal recovery drill | Annual full rebuild from scratch on fresh hardware | Recovery runbook + test server + documented results | No recovery drill ever conducted | Provision temporary server, execute full runbook, document results, fix gaps | Annual drills completed | 1 | 0
Immutable backup copy | Write-once backup that cannot be ransomware-encrypted | Backblaze B2 Object Lock or Hetzner Storage Box immutable mode | No immutable backups exist | Enable Object Lock on B2 bucket, configure retention policy, verify immutability | Immutable backup copies | 1 | 0
Recovery time objective (RTO) validation | Validated RTO of 4 hours for Level 1 recovery | Timed drill + documented recovery steps | RTO never measured | Conduct timed recovery drill, document each step duration, optimise bottlenecks | Measured RTO (hours) | 4 | 999
2. Self-Repair Agent
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Error detection & classification | Every agent automatically detects, classifies (recoverable/catastrophic), and logs errors | Structured error handler wrapping all agent functions | No standardised error handling across agents | Build base_agent.py with try/except wrapper, error classification enum, structured logging | Agents with error detection (%) | 100 | 0
Knowledge Base lookup on error | Agent queries Vault (4,663 files) via Qdrant for known solutions on any error | Qdrant semantic search + keyword fallback with >85% confidence threshold | Qdrant has 57,434 vectors but no agent-error lookup pathway | Build kb_lookup.py function, integrate into error handler, set 85% confidence gate | KB lookup success rate (%) | 85 | 0
First fix attempt from KB | Apply KB-recommended fix, verify, log resolution | Automated fix application + verification checks | No automated fix application exists | Build fix_applier.py: parse KB solution, apply, run verification, log outcome | First-fix resolution rate (%) | 60 | 0
Second fix attempt (alternative strategy) | Try alternative approach with modified parameters or fallback provider | Multi-strategy resolver with parameter adjustment | No alternative strategy logic exists | Build alt_strategy.py: parameter variation, provider fallback (Ollama↔LiteLLM), log both attempts | Second-fix resolution rate (%) | 25 | 0
SearXNG deep research escalation | Construct targeted search query, find solution from docs/GitHub/SO, synthesise fix | SearXNG API integration + LLM synthesis | SearXNG running on port 8888, not integrated with agent error flow | Build searxng_researcher.py: construct query from error context, search, LLM-synthesise solution | Research resolution rate (%) | 10 | 0
Structured human escalation | Package full context + all attempts + recommended next steps, escalate via Pulse | Telegram notification with structured error package | Telegram bot exists (@codesovbot) but no structured escalation format | Build escalation_packager.py: format error context, attempts, recommendations; send via Telegram | Escalations with full context (%) | 100 | 0
Resolution logging to Knowledge Base | Every resolution (success or failure) creates/updates a KB entry for future use | Auto-write to Vault + re-embed in Qdrant | No automated KB enrichment from resolutions | Build kb_writer.py: generate markdown, write to vault, trigger re-embedding | KB entries from resolutions (per month) | 50 | 0
Graceful degradation mode | Agent enters reduced functionality (not crash) when all repair attempts fail | Degradation state machine with partial service maintenance | Agents crash on unhandled errors | Build degradation_mode.py: define reduced-service states per agent type, maintain core functions | Agents with graceful degradation (%) | 100 | 0
Autonomous self-repair rate tracking | Track and report overall self-repair rate, target >95% within 6 months | Prometheus metrics + Grafana dashboard | No repair metrics exist | Instrument all repair steps with Prometheus counters, build Grafana self-repair dashboard | Autonomous repair rate (%) | 95 | 0
Chaos engineering tests | Quarterly deliberate failure injection to validate self-repair | Chaos test suite with controlled failure scenarios | No chaos testing exists | Build chaos_suite.py: inject API failures, DB timeouts, model errors; verify cascade handles all | Chaos tests per quarter | 10 | 0
3. AI Board Testing
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
5-seat board architecture deployment | 5 AI agents (CEO/COO/CFO/CTO/Nemesis) with distinct models deployed and callable | LangGraph/AutoGen multi-agent framework on Beast | Architecture specified but no agents deployed | Deploy 5 agent containers, wire LiteLLM routing (Opus/Llama70B/GPT-4.1-mini/Sonnet/Gemini) | Board agents deployed | 5 | 0
Believability-weighted voting protocol | 6-step deliberation: independent → collation → deliberation → weighted vote → pre-mortem → commit | Facilitator agent (Llama 8b) coordinating 6-step protocol | Protocol specified, not implemented | Build facilitator.py implementing all 6 steps, independent-first with anchoring instruction | Deliberation protocol steps implemented | 6 | 0
Baseball Card system | Rolling 90-day performance profiles per agent per domain, Bayesian posterior updates | FalkorDB Baseball Card nodes + update triggers | JSON schema defined, no storage or update logic | Build baseball_card.py: create FalkorDB nodes, implement Bayesian update on decision outcomes | Agents with active Baseball Cards | 5 | 0
Synthetic test generation (Phase 1) | 2,000 factual accuracy + 2,000 advice quality + 1,500 honesty tests generated | LLM-generated test cases from 4 sources with human review | No test cases exist | Build test_generator.py: generate from master doc, client scenarios, adversarial, cross-domain | Test cases generated | 10000 | 0
Phase 1 execution — synthetic data | All 10,000 tests run against Board with all metrics above minimum thresholds | Automated test harness with 5-dimension scoring | No test harness exists | Build test_harness.py: run tests, score accuracy/honesty/safety/speed/impact, report results | Phase 1 tests passed (%) | 90 | 0
Phase 2 — anonymised historical data | Board accuracy matches or exceeds baseline on real (anonymised) client scenarios | Anonymisation pipeline + historical case replay | No anonymisation pipeline or historical data prepared | Build anonymiser.py, collect historical decisions, replay through Board, compare outcomes | Phase 2 accuracy vs baseline (%) | 100 | 0
Phase 3 — live shadow mode | AI Board runs parallel to human decisions for 90 days, outperforms | Shadow mode runner with comparison logging | No shadow infrastructure exists | Build shadow_runner.py: intercept decisions, run through Board silently, log comparison | Shadow mode days completed | 90 | 0
Dissent tracking and accuracy | All dissenting opinions logged and tracked against actual outcomes over time | FalkorDB dissent nodes with outcome edges | No dissent tracking exists | Build dissent_tracker.py: log dissents, link to outcomes, calculate dissent accuracy rate | Dissent accuracy tracking (%) | 100 | 0
Decision audit log | Every Board decision recorded to FalkorDB with full reasoning chains | FalkorDB Decision nodes + temporal edges + reasoning storage | FalkorDB running but no decision schema | Create Decision node schema, build audit_logger.py, store all reasoning chains | Decisions with full audit trail (%) | 100 | 0
Cognitive anchoring prevention | Independent-first protocol prevents sycophancy and Mandela Effect contamination | Anchoring instruction in prompts + independent isolation | Not implemented | Add cognitive anchoring instruction to all agent prompts, enforce independent generation | Anchoring compliance (%) | 100 | 0
4. Client Onboarding
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Radical honesty contract signing | Every client signs radical honesty contract before engagement begins | Digital contract with e-signature (DocuSign/PandaDoc) | Contract exists as concept, no digital version | Draft contract in PandaDoc, include no-redundancy clause and exit clause, test e-sign flow | Clients with signed contract (%) | 100 | 0
Pre-onboarding boss conversation | Structured conversation covering process, timeline, Trust Ladder, communication preferences | Onboarding checklist + meeting template | Ad-hoc conversations, no structure | Build structured meeting template, checklist of 6 topics, record preferences in CRM | Onboarding meetings with full checklist (%) | 100 | 0
Forensic data extraction (Days 1-3) | Extract ALL data from legacy systems — email, files, databases, CRM, accounting | Extraction toolkit: IMAP/API connectors + audit trail | No standardised extraction toolkit | Build extraction toolkit with connectors for common SMB systems (Xero, Mailchimp, Google), copy-never-cut, full audit log | Data sources extracted per client | 8 | 0
Voice & Tone capture | Analyse email/comms patterns, build voice profile, PUDDING engine processes across 2,401 categories | PUDDING engine semantic analysis | PUDDING engine specified but not deployed | Deploy PUDDING, feed client communications, generate voice profile, validate with boss | Voice profiles generated | 1 | 0
Silent observation period (24-48h) | System observes without changes, builds gap analysis: current vs best practice | Automated gap analysis generator | No automated gap analysis tool | Build gap_analyser.py: compare extracted data against ISO 9001 best practice, rank by impact | Gap analysis items identified per client | 20 | 0
Change proposal to boss | Present gap analysis with ranked recommendations, boss decides pace and scope | Structured proposal document + priority matrix | No structured proposal format | Build proposal_generator.py: gap analysis → ranked recommendations → visual priority matrix | Proposals with ranked recommendations (%) | 100 | 0
Staff Trust Ladder — Step 1: Rumour control | Address fears before AI is introduced, via boss communication | Boss communication script + FAQ document | No staff communication materials | Write communication templates: what AI will/won't do, no-redundancy guarantee, FAQ | Staff receiving pre-introduction comms (%) | 100 | 0
Staff Trust Ladder — Step 2: First encounter (voice-first) | AI introduces itself by voice, admits what it is, demonstrates honesty | Voice-first interaction via WhatsApp/Telegram voice note | No voice-first introduction capability | Build voice_intro.py: generate personalised voice introduction using client's AI voice profile | Staff with voice-first introduction (%) | 100 | 0
Staff Trust Ladder — Step 3: Quick win demonstration | AI performs a useful task for each staff member in first interaction | Automated task detection + completion | No quick-win system | Build quick_win.py: detect easiest friction point per staff member, resolve it, show result | Staff experiencing quick win in day 1 (%) | 90 | 0
Staff Trust Ladder — Step 4: Privacy guarantee | Staff receive clear privacy SLA — training data PRIVATE, boss never told | Staff-AI privacy SLA document + technical enforcement | No privacy SLA exists | Draft privacy SLA, implement technical walls (boss cannot access staff training data), prove it | Staff with signed privacy SLA (%) | 100 | 0
Staff Trust Ladder — Step 5: Life goals conversation | With layered consent, AI explores staff life goals to align support | 3-question layered interview (problems → interests → goals) | Interview structure defined, not implemented | Build layered_interview.py: implement 3 questions with consent gates, store goals securely | Staff with life goals captured (%) | 80 | 0
Onboarding cycle completion | Full cycle from contract to operational AI-augmented business in 14-24 business days | Project management template with milestone tracking | No standardised timeline or milestones | Build onboarding_project.py: Gantt chart template, milestone gates, automated progress alerts | Onboarding cycle time (business days) | 24 | 999
Staff adoption rate measurement | Track and report staff adoption at 30/60/90 days post-onboarding | Usage analytics + adoption dashboard | No adoption tracking | Build adoption_tracker.py: log AI interactions per staff member, report daily/weekly, dashboard | Staff adoption at 90 days (%) | 91 | 0
5. Data Sovereignty
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
UK GDPR compliance audit | Full GDPR compliance audit documented and reviewed quarterly | Compliance checklist aligned to UK GDPR + DUAA | Informal compliance, no documented audit | Build GDPR checklist covering all 7 principles, document current status, schedule quarterly review | Compliance audit score (%) | 100 | 50
DUAA Article 22A-22D compliance | Automated decision-making transparency: clear notice + right to contest + human intervention | Transparency framework for AI-assisted decisions | Not assessed against new DUAA provisions | Map all AI decision points, implement notice mechanism, contest pathway, human override | AI decisions with DUAA-compliant notice (%) | 100 | 0
Cyber Essentials April 2026 readiness | Full compliance with updated CE requirements: MFA everywhere, 14-day patching, cloud scope | CE compliance tracker with automated verification | MFA enforced, patching manual, no formal CE assessment | Automate patch tracking (14-day SLA), verify all cloud services in scope, prepare CE+ application | CE requirements met (%) | 100 | 80
Data flow sovereignty verification | All client data verified as never leaving EU jurisdiction at any point | Data flow map + automated egress monitoring | Architecture is EU-only but no formal verification or monitoring | Build data_flow_map.py: document every data path, deploy egress monitor (iptables logging), alert on non-EU destinations | Data flows verified as EU-only (%) | 100 | 90
Encryption at rest (LUKS + application-level) | Full-disk LUKS encryption + per-field encryption for sensitive client data | LUKS + application-level field encryption | LUKS on Beast, no per-field application encryption | Implement field-level encryption for PII fields in FalkorDB/Qdrant payloads, key rotation quarterly | Sensitive fields encrypted (%) | 100 | 50
Client data deletion on termination | All client data verifiably deleted within 30 days of contract termination | Automated deletion workflow with cryptographic verification | Manual deletion process, no verification | Build deletion_workflow.py: identify all client data locations, delete, verify with hash comparison, generate certificate | Terminations with verified deletion (%) | 100 | 0
No-training guarantee enforcement | Technical proof that client data is never used for model training | Ollama runs local-only, no fine-tuning pipeline, documented proof | True in practice but not formally documented or verified | Document Ollama config (no training endpoints), audit Docker network isolation, publish technical proof | Training guarantee documented | 1 | 0
Subject Access Request (SAR) process | Automated SAR response within 30 days with complete data export | SAR handler with automated data collection across all stores | No SAR process exists | Build sar_handler.py: query all data stores for subject, compile export, generate response letter | SAR response time (days) | 30 | 999
Data sovereignty as sales differentiator | Sovereignty messaging in all sales materials with verifiable proof points | Sales deck + proof-of-sovereignty demo | Mentioned in pitch but no structured proof materials | Build sovereignty_demo: show data flow map, Hetzner EU location, Ollama local inference, zero-telemetry proof | Prospects receiving sovereignty demo (%) | 100 | 0
6. Behavioural Psychology
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Partner model positioning (not friend-like) | AI consistently positioned as egalitarian trusted advisor with defined boundaries | Prompt engineering + behavioural guidelines in system prompts | Concept defined, not implemented in agent prompts | Embed partner-model instructions in all agent system prompts, test for boundary compliance | Agents with partner-model prompts (%) | 100 | 0
Disclosed manipulation framework | Staff told upfront: 'We are nudging you toward your goals — and we admit it' | Onboarding script + recurring transparency reminders | Concept defined, no implementation | Write disclosure script for staff onboarding, build periodic transparency reminder messages | Staff receiving disclosure (%) | 100 | 0
Metric reframing implementation | All metrics presented as 'X away from goal' not 'Y% complete' | Metric reframing engine in The Pulse dashboard | Not implemented in any interface | Build metric_reframer.py: convert all % metrics to gap-to-goal format in Pulse UI | Metrics using gap-to-goal framing (%) | 100 | 0
No-red-indicator policy in The Pulse | Health indicators use green/amber/muted grey only — never red | Colour system enforcement in all UI components | Designed for The Pulse, not enforced elsewhere | Audit all UI components, replace red indicators, implement colour policy as CSS/design-system rule | UI screens compliant with no-red policy (%) | 100 | 0
Haggis gamification (The Pudding) | 8-stage haggis character responding to task completion streaks | React/SVG component with 8 visual stages + rotating phrases | Designed and prototyped, not deployed to production | Deploy Pudding component to production Pulse, connect to task completion API, test all 8 stages | Pudding deployed to production | 1 | 0
AI absolute boundaries enforcement | AI never pushes back, never offers opinions, never does HR, always says 'I don't know' when unsure | Boundary compliance testing + automated checks | Boundaries defined in spec, no automated testing | Build boundary_tester.py: test each boundary with adversarial prompts, run weekly, alert on violations | Boundary compliance rate (%) | 100 | 0
Staff-AI Service Level Agreement | Formal SLA defining AI response times, availability, privacy, and limitations | SLA document + automated SLA monitoring | No SLA exists | Draft SLA covering response time (<5s), uptime (99.5%), privacy guarantees, limitation disclosures | Staff with active SLA (%) | 100 | 0
Training privacy enforcement | Staff training interactions PRIVATE — boss never told, technically provable | Technical isolation of training data with access controls | Privacy concept defined, no technical enforcement | Implement role-based access: staff training data in isolated Qdrant namespace, boss account excluded | Training sessions with enforced privacy (%) | 100 | 0
Life goals data protection | Life goals data used ONLY to help staff, never for performance management | Purpose-limitation controls + audit trail | Life goals concept defined, no data controls | Build purpose_limiter.py: flag life-goals data, prevent inclusion in any performance report, audit access | Life goals data access violations | 0 | 999
Humour calibration (jokes go slow) | AI earns right to joke with individuals over time, can joke about Ewan from start | Humour progression system based on relationship tenure | Not implemented | Build humour_calibrator.py: track interaction count per person, unlock joke tiers gradually | Staff with calibrated humour profile (%) | 100 | 0
7. Convergence Pipeline
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Drop Zone directory structure | Create /data/convergence/ with inbox/processed/failed/schemas/ directories | Filesystem setup on Beast | Directory structure does not exist on Beast | SSH to Beast, create directory structure, set permissions, document in runbook | Drop Zone directories created | 4 | 0
Canonical JSON schema + Pydantic validation | All research output validated against canonical schema before ingestion | Pydantic model enforcing all schema rules | Schema defined in spec, no Pydantic model deployed | Build canonical_schema.py: Pydantic model with all validation rules, deploy to convergence service | Schema validation deployed | 1 | 0
File watcher (inotifywait/Temporal) | Automatic trigger when new files arrive in inbox | inotifywait wrapper or Temporal cron schedule | No file watcher exists | Deploy inotifywait-based watcher, trigger Temporal workflow on new .json file in inbox | File watcher operational | 1 | 0
Document deduplication (SHA-256) | Duplicate documents detected and skipped via content fingerprinting | SHA-256 fingerprint + Redis SET check | No deduplication exists | Build dedup_document.py: SHA-256 hash, Redis SET lookup, skip duplicates, move to processed | Duplicate detection accuracy (%) | 100 | 0
Entity extraction (LLM structured output) | Extract entities beyond input JSON using seed-concept approach | LiteLLM + Pydantic structured output + seed concepts from FalkorDB | No entity extraction pipeline exists | Build extract_entities.py: fetch top-100 existing entities as seeds, LLM extraction with structured output | Entity extraction precision (%) | 90 | 0
4-tier entity resolution | Exact → Alias → Semantic (≥0.92) → LLM judge linking for all entities | Four-tier resolution algorithm with merge audit trail | No entity resolution exists | Build entity_resolver.py: implement all 4 tiers, normalisation rules, post-batch resolution, merge logging | Entity resolution accuracy (%) | 95 | 0
Fact-level deduplication | Triple hashing (subject¦predicate¦object) prevents duplicate facts | Triple hash + Redis SET + source_count increment | No fact deduplication exists | Build dedup_facts.py: normalise triples, hash, check Redis, increment source count on duplicates | Fact dedup accuracy (%) | 95 | 0
Dual-write to FalkorDB + Qdrant (atomic) | Atomic write to both stores in same Temporal activity, rollback on failure | Temporal activity with dual-write + rollback | Separate ingestion paths, no atomic writes | Build dual_writer.py: single Temporal activity writing to both stores, rollback semantics | Dual-write atomicity (%) | 100 | 0
Unified Qdrant collection migration | Replace 4 collections with single amplified_knowledge (768d nomic-embed-text) | Migration scripts + re-embedding + verification | 4 incompatible collections exist (384d/768d mixed) | Build migration scripts, re-embed all 14,581 + 57,434 vectors at 768d, verify search quality | Collections unified | 1 | 0
Vault backfill (4,422 files) | Complete vault ingested into unified pipeline | add_episode_bulk for initial load + incremental for ongoing | 541 files loaded via direct-load, no extraction performed | Fix graph name (amplified), increase timeout to 60s, run full backfill, monitor progress | Vault files ingested (%) | 100 | 12
Telegram notification on ingestion | Ewan receives summary after every batch: entities, facts, duplicates, conflicts | Telegram bot integration in Temporal workflow | Telegram bot exists but not connected to convergence | Build notify_telegram.py: format summary, send via @codesovbot, include conflict flags | Ingestion batches with notification (%) | 100 | 0
Conflict resolution (temporal/numerical/factual) | Systematic resolution: temporal succession, weighted median, dual-record with conflict_group | Conflict resolver with 3 strategies | No conflict resolution exists | Build conflict_resolver.py: implement 3 strategies, flag conflicts for review, log resolutions | Conflicts resolved automatically (%) | 80 | 0
8. The Pulse
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Glance view (5-second comprehension) | 3 tasks + health dots + 1 line AI text — comprehensible in 5 seconds | React Native / responsive web component | Designed, not deployed to production | Build Pulse Glance component: 3 task cards, health dot indicators, single AI insight line | Glance comprehension time (seconds) | 5 | 999
Morning view (2-3 minute daily briefing) | Full health indicators, tasks, overnight summary, haggis, AI conversation | Extended dashboard pulling from all data sources | Designed, not deployed to production | Build Pulse Morning component: health grid, task list, overnight digest, Pudding, chat interface | Morning view data sources connected | 7 | 0
Glance ↔ Morning transition | Seamless pull-down/push-up transition between views with no mode selection | CSS animation + gesture detection | UI prototype exists, not production-ready | Implement pull-down animation, gesture handler, state persistence between views | Transition smoothness (60fps) | 1 | 0
Health indicators (green/amber/grey only) | 7 business health indicators using approach-framing colour system | Data pipeline from client systems → health scoring → colour assignment | No health scoring pipeline | Build health_scorer.py: connect to client data (Xero, Google, CRM), calculate 7 health scores, assign colours | Health indicators operational | 7 | 0
Tooltip language (opportunity framing) | Tooltips use gain-framing: 'room to strengthen' not 'declining' | Content template engine with approach-oriented language | Not implemented | Build tooltip_templates.py: gain-framed language for all health states, A/B test with users | Tooltips using approach framing (%) | 100 | 0
Task generation and prioritisation | AI generates 3 prioritised daily tasks based on business state and goals | Task engine: gap analysis → priority scoring → top 3 selection | No task generation engine | Build task_engine.py: analyse business gaps, score by impact/urgency, select top 3, present in Pulse | Tasks generated with AI reasoning (%) | 100 | 0
9. Amplified Machine
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Swanson discovery engine deployment | Literature-Based Discovery running on Beast, finding hidden connections | swanson-engine Docker container with Qdrant integration | 66 Python files deployed but untested, generated without Beast infrastructure | Validate all 66 files against Beast APIs, fix imports, run integration tests, rebuild container | Swanson engine files validated (%) | 100 | 0
Content Factory pipeline | Research → Content Generation → Validation Gate → Distribution | LangGraph workflow with 4 nodes | LangGraph core container specified but not tested | Test each node independently, wire end-to-end, validate output quality with sample content | Pipeline nodes operational | 4 | 0
Nature's Intelligence algorithms | Quorum Sensing + Slime Mold + Viral SIR + Bacterial Foraging operational | 4 nature-inspired algorithm modules | Code exists but never tested on real data | Unit test each algorithm, feed sample marketing data, validate output is sensible, tune parameters | Nature algorithms validated | 4 | 0
Missing worker tasks deployment | 8 missing worker files deployed and tested | Worker task modules for content, monitoring, email, video, etc. | 8 worker task files missing | Write missing workers using Beast's own infrastructure (Ollama, SearXNG), deploy, smoke test | Missing workers deployed | 8 | 0
Empty __init__.py stubs filled | 6 __init__.py files with proper imports and module exports | Module initialisation with correct import structure | 6 __init__.py files are empty stubs | Audit each module, determine required exports, fill __init__.py files, test imports | Init files completed | 6 | 0
Kaizen continuous improvement cycle | Automated content performance analysis feeding back into strategy | Kaizen node in LangGraph with performance data input | Kaizen node exists in code but no feedback loop | Connect kaizen.py to analytics data, implement feedback scoring, auto-adjust content strategy | Kaizen cycles completed (per month) | 4 | 0
10. Advocate System
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Intelligence gathering layer | 4-layer system: gather → process → create → advocate | Multi-source intelligence pipeline | Specified in Advocate Specification, not deployed | Build intelligence_gatherer.py: connect to SearXNG, social APIs, news feeds, competitor monitors | Intelligence sources connected | 5 | 0
65% confidence threshold enforcement | All advocacy content must meet 65% confidence before publishing | Confidence scorer with hard gate | Threshold defined, no scorer built | Build confidence_scorer.py: multi-factor confidence calculation, hard gate at 65%, log rejections | Content meeting confidence threshold (%) | 100 | 0
Radical attribution | Every piece of content attributes its sources and AI involvement | Attribution engine embedding source references | Attribution principle defined, no engine | Build attribution_engine.py: track all sources through pipeline, embed attributions in output | Content with full attribution (%) | 100 | 0
GitHub Bridge for technical advocacy | Automated contribution to relevant open-source projects | GitHub API integration for PR/issue creation | Concept specified, not implemented | Build github_bridge.py: monitor relevant repos, identify contribution opportunities, draft PRs | GitHub contributions (per month) | 4 | 0
11. Beast Infrastructure
Process | Ideal | Solution | Where They Are | How We Do It | KPI | Target | Current
Fix Graphiti ingestion (CRITICAL) | Graph name aligned, timeouts resolved, 3,234 remaining files ingested | Fix graph name to 'amplified', increase timeout to 60s, resume ingestion | 51 failures, 0 successes; amplified_brain graph empty; amplified graph has 13,004 nodes | Change GRAPH_NAME to 'amplified', set FalkorDB timeout 60000ms, rebuild FT index, relaunch | Vault files in FalkorDB (%) | 100 | 6
Fix unhealthy Docker containers | All 29+ containers healthy with no restart loops | Container health audit + configuration fixes | ch-pipeline and enforcer containers unhealthy | Inspect logs for ch-pipeline and enforcer, fix configs, verify health checks pass | Unhealthy containers | 0 | 2
Prometheus monitoring deployment | Full monitoring stack: Prometheus metrics from all services + Grafana dashboards | prometheus.yml + service exporters + Grafana | prometheus.yml missing, monitoring not configured | Write prometheus.yml with all service targets, deploy exporters, build core Grafana dashboards | Services monitored by Prometheus | 29 | 0
Ollama model validation | All 4 models (qwen3-coder:30b, llama3.1:70b, llama3.1:8b, nomic-embed-text) responding correctly | Model health check + inference quality tests | Models loaded but inference quality not validated | Build model_healthcheck.py: test each model with standard prompts, verify quality, benchmark speed | Models validated | 4 | 0
Amplified Machine code validation | All 66 deployed Python files syntax-checked, import-tested, and smoke-tested | Automated validation suite using Beast's own tools | Code generated without using Beast infrastructure, untested | Run pylint/mypy on all 66 files, fix errors, run import tests, basic smoke tests with Ollama review | Files passing validation (%) | 100 | 0
Local inference ratio optimisation | 60%+ of all AI inference running on local Ollama models (not cloud APIs) | LiteLLM routing rules prioritising local models | LiteLLM configured but routing not optimised for local-first | Audit current routing, adjust LiteLLM config to route COO/Facilitator/embedding to Ollama, measure ratio | Local inference ratio (%) | 60 | 0
Cove orchestrator production readiness | Telegram bot handling all commands, Temporal workflows stable, prompts seeded | Cove stack (API + worker + Temporal + PostgreSQL) | Cove responding to commands, Layer 0+1 prompts seeded, Temporal operational | Complete Layer 2 (business brain) prompts, wire agent tools, test all /build scenarios end-to-end | Cove commands operational | 6 | 3

## Coding Solutions
Process | Solution Type | Technology Stack | Pre-Built Option | Build Effort (days) | Priority
Error detection & classification | Custom Python module | Python + structlog + Pydantic | Sentry (error tracking SaaS) — free tier for 5k events/month | 3 | CRITICAL
KB lookup on error | Custom Python module | Qdrant Python client + sentence-transformers | LangChain RetrievalQA — pre-built retrieval chain | 2 | CRITICAL
Self-repair cascade | Custom Python module | Python + Temporal activities | LangGraph ToolNode with retry — handles tool failures | 5 | CRITICAL
SearXNG research escalation | API integration | SearXNG REST API + LiteLLM | Tavily API (pre-built research) — but not self-hosted | 2 | HIGH
Canonical schema validation | Pydantic model | Pydantic v2 + JSON Schema | Use Pydantic directly — no pre-built alternative needed | 1 | CRITICAL
Entity extraction pipeline | LLM pipeline | LiteLLM + Pydantic structured output | LangChain create_extraction_chain — pre-built entity extraction | 3 | HIGH
4-tier entity resolution | Custom Python module | spaCy + sentence-transformers + FalkorDB | Dedupe (Python library) — open-source entity resolution | 5 | HIGH
Dual-write FalkorDB + Qdrant | Temporal activity | Temporal Python SDK + Graphiti + Qdrant | No pre-built; Temporal provides rollback semantics | 3 | HIGH
Believability-weighted voting | Multi-agent framework | LangGraph + LiteLLM + FalkorDB | AutoGen (Microsoft) — pre-built multi-agent framework | 7 | HIGH
Baseball Card system | Graph data model | FalkorDB Cypher + Bayesian update | No pre-built; custom Bayesian posterior in Python/NumPy | 3 | MEDIUM
10,000 test generation | LLM pipeline | Claude/GPT-4.1 + Pydantic test schema | DeepEval — open-source LLM testing framework | 5 | HIGH
Forensic data extraction toolkit | Integration suite | Python + IMAP + REST APIs (Xero, Google, Mailchimp) | Airbyte — open-source data extraction platform | 10 | HIGH
PUDDING voice profile engine | NLP pipeline | spaCy + sentence-transformers + custom taxonomy | No pre-built equivalent; custom NLP pipeline needed | 15 | MEDIUM
Gap analysis generator | Analysis engine | Python + Pandas + ISO 9001 rubric | No pre-built; custom scoring against best practice benchmarks | 5 | HIGH
Staff adoption tracker | Analytics module | PostgreSQL + Grafana + custom event logging | Mixpanel/Amplitude (SaaS analytics) — but breaks data sovereignty | 3 | MEDIUM
Metric reframing engine | UI component | React/TypeScript + calculation module | No pre-built; simple arithmetic transform (target - current) | 1 | MEDIUM
Haggis (Pudding) component | React SVG component | React + SVG + CSS animations + Framer Motion | Already prototyped — deploy to production Pulse | 2 | MEDIUM
Health scoring pipeline | Data pipeline | Python + Xero API + Google API + scoring engine | No pre-built; custom pipeline connecting to SMB data sources | 7 | HIGH
Pulse task engine | AI module | LangGraph agent + client data + priority scoring | No pre-built equivalent for SMB-specific task generation | 5 | HIGH
Prometheus monitoring | DevOps | Prometheus + Grafana + Docker exporters | Prometheus is pre-built; configure prometheus.yml + exporters | 2 | CRITICAL
SAR handler | Compliance tool | Python + multi-store query + document generator | OneTrust/TrustArc (SaaS) — expensive, breaks sovereignty | 5 | MEDIUM
Deletion workflow | Compliance tool | Python + multi-store purge + hash verification | No pre-built with cryptographic verification | 3 | MEDIUM
Boundary compliance tester | Testing framework | Python + adversarial prompt library + assertion checks | DeepEval or Promptfoo — open-source LLM testing | 3 | MEDIUM
Humour calibrator | Relationship tracker | Python + interaction counter + tier unlock logic | No pre-built; simple state machine with time-decay | 1 | LOW
Data flow egress monitor | Security tool | iptables logging + Python parser + alerting | Falco (CNCF) — open-source runtime security | 2 | HIGH
Cove Layer 2 business brain | Prompt engineering | PostgreSQL business_prompts + Temporal | Already partially built in Cove; complete remaining prompts | 3 | HIGH
LiteLLM local-first routing | Configuration | LiteLLM YAML config + routing rules | LiteLLM proxy has built-in routing — just configure | 1 | HIGH
Voice-first staff introduction | Audio generation | TTS API (Ollama/local) + WhatsApp/Telegram API | ElevenLabs or Bark (open-source TTS) | 3 | MEDIUM
Quick win task detector | AI module | Python + client data analysis + task selection | No pre-built; custom analysis of friction points per person | 3 | MEDIUM
Conflict resolver (3 strategies) | Data pipeline | Python + temporal logic + weighted median | No pre-built; custom implementation of 3 resolution strategies | 4 | MEDIUM